## Risk Matrix
Asset | Threat | Vulnerability | Impact | Likelihood | Risk Level | Recommended Control | NIST CSF Mapping
EHR System | Ransomware Attack | Unpatched software | High | High | Critical | Regular patching, EDR, daily backups | Protect, Recover
Patient Portal | Unauthorized Access | Weak passwords | High | Medium | High | MFA, password policy | Protect, Identify
Workstations | Malware Infection | Unrestricted internet access | Medium | High | Medium | Network segmentation, web filtering | Detect, Protect
Cloud Storage | Data Breach | Misconfigured permissions | High | Medium | High | Access review, encryption, audit logging | Protect, Detect
Medical Devices | Lateral Movement | Outdated firmware | Medium | Medium | Medium | Network isolation, patch schedule | Protect, Identify
Employees | Phishing | Lack of awareness training | High | High | Critical | Phishing simulations, quarterly training | Identify, Protect, Respond
Prepared by Taniesha Stewart – 2025

## Risk Register
Risk ID | Title | Description | Owner | Impact | Likelihood | Risk Level | Status | Mitigation Plan | Target Date | NIST CSF Mapping
1 | EHR Unauthorized Access | Unauthorized access to patient EHR | IT Security | High | Medium | High | Open | Implement MFA, review logs | 2025-11-30 | Protect, Detect
2 | Staff Phishing | Successful phishing leading to credential theft | Compliance | High | High | Critical | Open | Quarterly phishing simulations and training | 2025-10-31 | Identify, Protect, Respond
3 | Device Firmware | Outdated medical device firmware | Clinical Engineering | Medium | Medium | Medium | Open | Implement patch schedule and vendor coordination | 2025-12-15 | Protect, Identify
Prepared by Taniesha Stewart – 2025

## Vulnerability Summary
System | Scan Date | Critical Count | High Count | Medium Count | Low Count | Top Findings Summary | Remediation Deadline
EHR Server | 2025-10-01 | 3 | 5 | 8 | 2 | Outdated third-party components; missing patches | 2025-11-15
Web Portal | 2025-10-02 | 1 | 3 | 6 | 4 | Improper input validation and auth weaknesses | 2025-11-10
Workstations | 2025-10-05 | 0 | 2 | 5 | 10 | Outdated OS patches; missing EDR on some endpoints | 2025-11-20
Prepared by Taniesha Stewart – 2025

## Asset Inventory
Asset ID | Asset Name | Type | Owner | Location | Confidentiality | Integrity | Availability | Criticality | Notes
101 | EHR System | Application | Health IT | Data Center / Cloud | High | High | High | Critical | Hosted SaaS EHR
102 | Patient Portal | Web App | IT Security | Cloud | High | Medium | High | High | External-facing portal
103 | Workstation Fleet | Hardware | IT | All sites | Medium | Medium | Medium | Medium | Windows 10/11 endpoints
104 | Infusion Pumps | Medical Device (IoT) | Clinical Engineering | Clinic Locations | Medium | High | High | High | Vendor-managed firmware
105 | Cloud Storage | Infrastructure | IT Security | Cloud | High | High | High | Critical | Stores backups & PHI
Prepared by Taniesha Stewart – 2025